## Perspective
Agile Project CheckList
Project Name :
No | Perspective | Type | Content | Status | Operator | Operation Date | Comment
1 | Project/Team Management | Do | Do educate the staff
2 |  |  | Have a story wall/board
3 |  |  | Do start meeting on time
4 |  |  | Do Retrospectives and it needs to be more diligent
5 |  |  | Involve entire team in estimation meetings
6 |  |  | Team members volunteer for tasks (self-organizing team)
7 |  |  | Create Burn down chart to monitor sprint progress
8 |  |  | Keep team size max 9.
9 |  |  | Have different profiles in team
10 |  |  | Have tolerance for failure
11 |  | Do not | Do not micro-manage
12 |  |  | Do not postpone the meeting
13 |  |  | Do not think bug fixing is different to user story. Bug fixing can be defined as user story and implement on new sprint according to priority.
14 |  |  | Do not continually reorganize your teams
15 | Development | Do | Have short daily meeting to resolve current issues
16 |  |  | Need to follow agreed standards for development
17 |  |  | Try to Reuse
18 |  |  | Follow continuous integration
19 |  |  | Design deployment strategy well in advance
20 |  |  | All code must have unit tests
21 |  |  | All code must pass all unit tests before it can be released
22 |  |  | Every feature needs to be "Deployable"
23 |  | Do not | Do not design too much in detail
24 |  |  | Do not make long scrum
25 |  |  | Do not document in too detailed form
26 | Product Owner/Business User | Do | Do always plan like it’s the last week of the project
27 |  |  | Involve in continuous discussions with the team
28 |  |  | Keeping a customer close to stop the developers making decisions without true business understanding
29 |  |  | Set acceptance criteria for the stories so that team can use them as guideline to meet PO expectations.
30 |  | Do not | Do not expect constantly improving velocity
31 |  |  | Do not live apart from the team
32 | IS Management | Do | Manage change through continuous inspection, evaluation and adaption
33 |  |  | For the organization to do some custom changes and adopt instead of following as guidelines.
34 |  | Do not | Do not disrupt the process and impede your agile implementation with too detailed guidelines and metrics but for sure define basic activities and artifacts that are crucial for a successful implementation
35 | General Process | Do | Convert the user requirements into product backlog items.
36 |  |  | Product backlog is primarily managed by your product owner and contains a high-level view of all the work that your team must complete to create the product. Your product owner ranks the user stories in the product backlog.
37 |  |  | Team creates the sprint backlog, which contains a detailed list of all the tasks that your team must complete to finish the user stories for the sprint
38 |  |  | Do have daily standup meetings for the sprint
39 |  |  | Sprint review meeting (Showcase) to present completed work
40 |  |  | Sprint retrospective to learn from previous sprint
41 |  |  | Release planning to release product increments
Note on D12: For example: it might be good to have an analyst, a developer and a tester profile in the team.

## Ritual
Agile Project CheckList
Project Name :
No | Ritual | Type | Content | Status | Operator | Operation Date | Comment
1 | Planning ritual | Do | Split stories into tasks small enough so that would not be splited more and which would have a deliverable item when completed
2 |  |  | Decide the focus factor of team before the review meeting.
3 |  |  | Challenge yourself to increase your focus factor if you have succeeded 3 sprints with existing focus factor
4 |  |  | Decrease your focus factor if you have failed 3 sprints with existing focus factor
5 |  | Do not | Don't add buffers to the tasks, give pure effort hours to the tasks
6 | Daily ritual | Do | Stand up meeting style to keep this meeting short
7 |  |  | Have an exact time and place for the meeting
8 |  |  | Mention 3 points briefly; what you have done, what you will do and what is blocking you right now
9 |  |  | Have a sprint board, physical or online but have one
10 |  | Do not | Daily meeting must not be longer than 15 minutes
11 |  |  | Do not give details, talk details after daily meeting if needed only with required subset of team members
12 | Grooming ritual | Do | Involve entire team in estimations
13 |  |  | Try to split big stories into multiple stories
14 |  |  | Team members should propose new stories, they can be technical improvements, process improvements, tax (a story that should be done for continuity or a business story) and discuss in these meetings
15 | Review ritual | Do | Do demo if possible
16 |  |  | All team members share the demo responsibly in the meeting so that can actively join and take part
17 | Retrospective ritual | Do | Always do regularly
18 |  |  | Keep a list to maintain impediments and update it during the meeting
19 |  |  | Review metrics from time to time
20 | Sprint Overall | Do | Follow all rituals, you will see advantage of this in time
21 |  |  | Keep sprint length same as much as possible but may adopt if there are really important reasons coming from retrospectives
22 |  |  | Show demo to business representative when story was completed, you can make needed updates, changes before the review meeting
23 |  |  | Open story to business test or test of other parties when story was completed, you can make needed updates, changes before the review meeting
24 |  |  | Have a DoD list for tasks, stories, sprint and release and strictly follow it. only add the reasonable and sustainable items in the beginning and challenge yourself in time by adding more items to the list
25 |  |  | Keep importance to the metrics as they will show you how is your progress at the moment, how you can adopt in the future and what needs urgent action etc
26 |  |  | Have a burndown chart to monitor sprint status
Note on D5: Focus Factor as noted in GADC Development Common KPI (Agile) "Focus Factor is a measure of how much time engineers are spending doing actual work versus other responsibilities (like meetings, administrative tasks, etc.). It requires engineers to assign ‘ideal work hours’ to each task in a sprint." calculated by "Man-effort spent on acutal work/total man-effort for a release * 100%"
Note on D25: In agile it is better if you can display your completed work before review meeting so that you can make fixes or changes before the end of sprint. "story was completed" means development was finished and tested manually or automatically and ready to business validation/testing.
Note on D26: In agile sooner is always better. You can demo to PO in dev and ask Po test it before review meeting. By the time PO accepts the story in review meeting then it is relased to stg where SIT/ UAT can be initiated.